Group 4 – “Health is Wealth”

University of Surrey

AI & Health - EEEM069

28th February 2026

MEETING MINUTES [1]

Meeting Minutes: AI & Health Group 4

- Date & Time:

  - DAY: 26/02/2026

  - TIME: 6pm

- Attendance:

  - Lawal, Akeeb

  - Zannat Chowdhury

  - Akano Fiyinfoluwa

  - Golla, Poorna Chandra C

  - Jadhav, Pushkar Vijay V

  - Nampally, Giridhar Kumar

- Today’s Goal:

  - Basic Introduction of group members. Exchange of pleasantries

- Discussion Points:

  - Discussions on the next steps of the project,

    - Particularly regarding scheduled online meetings.

    - Deciding on a formal platform for work.

- Action Items (Who is doing what?):

  - Everyone: Read up on ELSA

  - Akeeb: Register on the UK data service link to gain access to the ELSA dataset

  - Fiyin: Creating a centralized document to help keep track of project objectives and tasks

- Next Meeting: TBD

MEETING MINUTES [2]

- Date & Time:

  - DAY: 8/04/2026

  - TIME: 10am

- Attendance:

  - Lawal, Akeeb

  - Zannat Chowdhury

  - Akano Fiyinfoluwa

  - Jadhav, Pushkar Vijay V

  - Nampally, Giridhar Kumar

- Today’s Goal:

  - Roadmap discussion and Task allocation

- Discussion Points:

  - Discussions on the next steps of the project,

    - What and how we will be doing our project.

    - Allocation of tasks .

- Action Items (Who is doing what?):

  - Everyone: Get hands on dataset of ELSA

  - Akeeb: Will be working on data preprocessing .

  - Fiyin: Will be working on model creation .

  - Zannat : working on data loading .

  - Pushkar : working on feature selection.

- Next Meeting: 10th April

MEETING MINUTES [3]

Date & Time:

DAY: 10/04/2026

TIME: 2pm

Attendance:

Lawal, Akeeb

Zannat Chowdhury

Akano Fiyinfoluwa

Golla, Poorna Chandra C

Jadhav, Pushkar Vijay V

Nampally, Giridhar Kumar

Today’s Goal:

Wave selection and methodology framing

Discussion Points:

Akeeb presented findings from his ELSA core wave audit (Waves 3–11).

Reviewed CES-D quality, participant overlap, and feature drift across waves.

Confirmed Waves 6, 7, and 8 form the strongest consecutive longitudinal block (>90% participant overlap, 93–97% valid CES-D responses).

Locked the modelling design: predict CES-D ≥ 3 at Wave 8 from Wave 6 and Wave 7 features (binary classification).

Agreed on Logistic Regression as the interpretable baseline, with Random Forest for non-linear comparison.

Noted IFS-derived variable files contain validated cesd_sc; agreed to use these rather than reconstructing from raw items.

Action Items (Who is doing what?):

Akeeb: Finalise the curated feature list from the audit (target ~30 predictors per wave).

Fiyin: Begin building the W6+W7 modelling pipeline; CES-D as primary outcome.

Zannat: Validate preprocessing assumptions on a single-wave baseline.

Pushkar: Investigate feature selection methods.

Giridhar & Poorna: Read up on classification evaluation metrics for imbalanced classes (ROC-AUC, F1, PR curves).

Next Meeting: 14/04/2026

MEETING MINUTES [4]

Date & Time:

DAY: 11/04/2026 – 13/04/2026

TIME: Async (GitHub Pull Request review)

Attendance:

Lawal, Akeeb (PR author)

Akano Fiyinfoluwa (reviewer)

Zannat Chowdhury (reviewer)

Today’s Goal:

Review and approve Akeeb's data audit notebook PR

Discussion Points:

Akeeb opened a pull request containing the full audit notebook and the curated feature list (modelling_features_final_curated.csv).

Reviewers verified reproducibility: notebook runs end-to-end on the team-shared dataset folder.

Confirmed wave selection rationale and the 30-feature funnel logic.

Minor comments raised on documentation; addressed by Akeeb in follow-up commits.

PR approved and merged; wave selection officially locked for downstream modelling.

Action Items (Who is doing what?):

Akeeb: Merge audit branch; tag latest commit as audit baseline.

Fiyin & Zannat: Pull merged audit branch into modelling work.

Next Meeting: 14/04/2026

MEETING MINUTES [5]

Date & Time:

DAY: 14/04/2026

TIME: 6pm

Attendance:

Lawal, Akeeb

Zannat Chowdhury

Akano Fiyinfoluwa

Jadhav, Pushkar Vijay V

Nampally, Giridhar Kumar

Today’s Goal:

Modelling progress check and CES-D scoring fix decision

Discussion Points:

Fiyin reported on the W6+W7 modelling pipeline build: data loading, merging, preprocessing, and initial Logistic Regression training all functional.

Issue raised: an earlier exploratory CES-D reconstruction (from raw PSced items, 0–3 scale) produced an apparent prevalence of ~74%, which is clinically implausible.

Investigation traced this to a scale mismatch: ELSA's CES-D items are binary (1 = yes / 2 = no after Stata recoding), not 0–3.

Resolution: switch to the IFS-validated cesd_sc variable (0–8 range). Prevalence corrects to ~19%, consistent with published ELSA estimates.

Discussed the design of a leakage sensitivity analysis (with vs. without prior CES-D as predictors) to test whether the model is just “depressed people stay depressed.”

Agreed to add SHAP analysis for model interpretability.

Action Items (Who is doing what?):

Fiyin: Implement the CES-D fix; add leakage sensitivity test; integrate SHAP explanations.

Zannat: Begin design of the enhanced pipeline (additional models, hyperparameter tuning, calibration).

Akeeb: Document the CES-D scoring lesson in CONTEXT.md.

Everyone: Review intermediate results before the next sync.

Next Meeting: 16/04/2026 (Fiyin & Zannat sub-team)

MEETING MINUTES [6]

Date & Time:

DAY: 16/04/2026

TIME: 3pm

Attendance:

Akano Fiyinfoluwa

Zannat Chowdhury

Today’s Goal:

Sub-team sync — review the enhanced pipeline and plan submission integration

Discussion Points:

Sub-team meeting between the modelling leads (Fiyin and Zannat).

Zannat presented the enhanced longitudinal pipeline: three prediction arms (W6, W7, W6+W7), five feature configurations per arm, four models (LR, RF, XGBoost, LightGBM), hyperparameter tuning via RandomizedSearchCV, and ensemble averaging.

Reviewed the SHAP “two-act” narrative: one analysis with the full feature set (showing prior CES-D dominance) and one without CES-D (revealing self-rated health, mobility, and financial difficulty as top independent predictors).

Agreed on the structure of the final submission notebook: single-file, run-once on Colab, with auto-installation of dependencies and one user-set ELSA_PATH variable.

Reviewed the leakage sensitivity numbers: AUC 0.85 with prior CES-D → 0.77 without. Agreed this is the central scientific finding.

Discussed presentation slide ordering and story arc.

Action Items (Who is doing what?):

Zannat: Finalise the submission notebook; add inline result interpretation between cells.

Fiyin: Draft the project report and presentation deck; integrate Akeeb's audit findings into the background section.

Both: Review the final notebook end-to-end before submission.

Next Meeting: Final integration before submission deadline